PNA Communication and Engagement Plan 2017-2018

From 1st April 2013, statutory responsibility for publishing and updating a statement of the need for pharmaceutical services passed to health and wellbeing boards (HWBs). Pharmaceutical Needs Assessments (PNAs) are used when considering applications for new pharmacies in an area and by commissioners to identify local health needs that could be addressed by pharmacy services. HWBs have a duty to ensure revised PNAs are in place by April 2018. The coordination and production of the pan-Lancashire PNA covering the three upper tier local authorities has been delegated to a steering group of partners. This collaborative approach gives ownership of the PNA process across the three localities and aims to encourage the widest range of stakeholders and those with an interest in the PNA to participate in its development.

| Author: PNA working group |
| --- |
| Version | Date | Status |
| 0.01 | 14 March 2017 | First draft for comments from Steering Group |
| 0.02 | 19 April 2017 | Approved for publishing |

The purpose of this plan is to ensure the timely delivery of key messages and actions at appropriate stages of PNA development which will take the form of briefings, update reports, links to national campaigns, formal consultation and stakeholder events over the course of the year so that HWBs and stakeholders have a clear understanding of the focus, process, and methodology of the PNA and have the opportunity to actively contribute to its development.

| Message/Action | Method | Stakeholders | Start date | End date | Frequency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PNA Awareness Raising article to explain what it is, who produces it, why and how it’s used? | Website article for HWB/JSNA sites (Check current website) Article in Community Pharmacy Lancashire weekly bulletin | Health Practitioners, Pharmacies, HWB members, Patients and Public | Mar 2017 | May 2017 | To be updated periodically | PNA Working Group rep in each locality Kath Gulson |  |
| Share project documents | Reports and project plan uploaded onto HWB/JSNA websites | Health Practitioners, Pharmacies, HWB members, Patients and Public | Mar 2017 | Mar 2018 | To be updated periodically | PNA Working Group rep in each locality |  |
| To ascertain the services provided by community pharmacies | Electronic Questionnaire via PharmOutcomes | Community Pharmacies | 4 May 2017 | 30 May 2017 | Once | PNA Steering Group |  |
| Comments on first iteration of PNA | Draft PNA | HWBs, NHS England, LPC, CCG, LPN, Public Health, Local Healthwatch | 15 October 2018 | 14 November 2018 | Once | PNA Steering Group |  |
| PNA Awareness Raising event – to coincide with the 60 day consultation | Stakeholder Event | HWB, NHS England, LPC, CCG, LPN, Public Health, CSU, Dispensing Doctors, Providers, Local Healthwatch, Patients and Public | Dec 2017 | Dec 2017 | Once | PNA Steering Group |  |
| Public engagement with 60 day consultation period | Social media – twitter and Facebook PNA hard copies placed in libraries and pharmacies across pan-Lancashire Attend Healthwatch events Engage with CVS | Public | Dec 2017 | Jan 2018 | As required | PNA Steering Group |  |
| Feedback on outcome of Consultation | Summary report and email to link to HWB/JSNA websites where it will be uploaded | HWB, NHS England, LPC, CCG, LPN, Public Health, CSU, Dispensing Doctors, Providers, Local Healthwatch, Patients and Public | Jan 2018 | Feb 2018 | Once | PNA Steering Group |  |
| Final version of PNA to be approved by each HWB | PNA, Report | HWBs | Feb 2018 | Feb 2018 | Once | PNA Steering Group |  |
| Disseminate final version of PNA | PNA and email link to HWB/JSNA websites where it will be uploaded | HWB, LPC, LPN, CCG, CSU, Local Healthwatch, Patients, Service users, Local Healthwatch, Public Health, Providers | Mar 2018 | Mar 2018 | Once | PNA Steering Group |  |
| Notification of amendments to PNA | Email link to PNA and amendments | HWB, LPC, LPN, CCG, CSU, Local Healthwatch, Patients, Service users, Local Healthwatch, Public Health, Providers | As req’d |  | As req’d | PNA Steering Group |  |

Risks

| Risk | Impact | Likelihood | How managed |
| --- | --- | --- | --- |
| Limited commitment from Board members and key partners | High | Low | Secure sign up and commitment early from HWB Chair and Members in each locality as early as possible Develop a clear set of key messages outlining the purpose and importance of PNAs Agree dates for updates and synchronise diaries as early as possible |
| Limited capacity to support development of the PNA | High | Medium | Secure sign up and commitment early from HWB Chair and HWB Members in each locality as early as possible Develop mechanism to alert HWB of capacity issues HWB to identify appropriate support for ongoing development as required |
| Arrangements for development of the PNA are not co-ordinated appropriately | High | Low/negligible | Set up a pan-Lancashire working group with appropriate expertise and experience to lead the process The working group will be supported by the HWBs officers to support co-ordination and awareness raising activities Set up regular working group meetings, devise a project plan with tasks assigned to relevant leads and produce a clear communications plan |
| The purpose/process of the PNA is not clear, well thought through or fully understood | High | Low | Driven through national guidance, which builds on existing PNAs with links to national campaigns Ongoing engagement with stakeholders to inform scope and content On-going discussion with LPN (LA) Subgroup and HWB updates at meetings |
| The PNA does not meet national guidelines and the expectations of HWBs |  | Low | Driven through national guidance, which builds on existing PNAs with links to national campaigns Secure support from local intelligence/analysts teams Continual dialogue and feedback through focus groups |