## Stakeholders
PNA STAKEHOLDERS
Name | Title | Contact email
Liz Petch |  | liz.petch@blackpool.gov.uk
Aidan Kirkpatrick |  | aidan.kirkpatrick@lancashire.gov.uk
Gifford Kerr |  | Gifford.Kerr@blackburn.gov.uk
Mike Walker |  | mike.walker@lancashire.gov.uk
Laura Wharton |  | Laura.Wharton@blackburn.gov.uk
Stephen Boydell |  | stephen.boydell@blackpool.gov.uk
Michael Rawsterne |  | michael.rawsterne@blackburn.gov.uk
Farhat Abbas |  | farhat.abbas@lancashire.gov.uk
Cathy Stuart | NHS England, Comms | cathystuart@nhs.net
Kath Gulson | CPL | kath@pharmacylancashire.org
Kerry Galloway | Healthwatch representative | Kerry.Galloway@healthwatchlancashire.co.uk
Emma Phillips | Pan-Lancashire CCG representative | Emma.Phillips@Blackpool.nhs.uk
Max Harrison | Senior Contracts Manager – Dental and Pharmacy | max.harrison@nhs.net
Mark Lindsay | Business Manager – Primary Care Commissioning | mark.lindsay@nhs.net

## Operational Plan
Executive Director:
Associate Director:
Lead:
Target Description: Production of Pharmaceutical Needs Assessment (PNA)
| Leadership | Duration (in working days) | Start Date | End Date | Orgnaisation responsible for completing task | Expected results/Notes | Achieved
1 | Each LA Lead to identify Exec Director and HWB member to ensure matrix input & ownership | 1 day | 14.02.17 | 14.02.17 | LAs | Check if Exec Director needed
2 | Paper to HWB to raise awareness of PNA and approval of Pan Lancs PNA steering group | 1 week | 07.02.17 | 30.04.17 | NHS England/Las | Engagement HWB /awareness of Judical Rw
3 | Pan-Lancashire PNA working group to be formed | 1 month | 1.1.17 | 1.2.17 | LA / NHS E | capacity and resource secured
4 | Stakeholder Workshop, inform process and development of PNA (stakeholders listed on next worksheet) | 1 month | 15.4.17 | 1.5.17 | Steering Group | Ensure stakeholder engagement & expertise | NA
People (capacity & workforce)
5 | Establish PNA Steering Group and Terms of Reference to meet monthly | 1 week | 01.02.17 | 10.2.17 | LA/ NHS E | Based on 2015 ToR
Process
6 | Define Pharmaceutical Services for purpose of PNA | 1day | 15.06.17 | 15.06.17 | NHS England | NHS England to provide pharmacy list
Assessment of Local Need
7 | Determine the most appropriate means of defining localities for PNA and produce statement how defined | 1 week | 1.3.17 | 8.3.17 | LA (S Boydell) | Statements from last PNAs. H&WB may have opinion. Localities are 12 districts in Lancs. & 2 unitary authorities |  | The PNA regulations requires the PNA to define ‘localities’ to use during this process. For the purpose of the Pan-Lancashire PNA the area is considered in terms of Lancashire County Council's 12 districts and the 2 unitary authorities of BwD and Blackpool. These localities were selected to support local decision making that takes into account the needs for the population in these areas; also see section 3.5. Characteristics of localities are further described in Appendix 2. Where appropraite, information will be presented at small geography level (ward, MSOA) to describe the health and wellbeing needs of local communities.
8 | Identify charactersitics of the population | 2 month | 10.2.17 | 31.03.17 | LA | Complete chapter 3
9 | Identify specific communities with poor health | 2 week | 1.04.17 | 18.08.17 | LA | Within chapter 5 |  | Contact to be made with commissioners and request pharmacies' commissiond services list on the 1/05/2017
10 | Benchmark localities against comparable populations | 2 week | 1.7.17 | 18.7.17 | LA | within chapter 4 - Comparison with pharmaceutical service provision elsewhere
11 | Identify patient and pharmacists perception of current and future pharmaceutical services | 2 months | 1.5.17 | 1.7.17 | LA/LPC | LG to send electronic survey via PharmOutcomes. KG to supprt LG. LP to explore Healthwatch sending out questionnaire to membership.
12 | Ensure Regulation 3G has been satisfied when assessing need | 1 month | 15.5.14 | 18.6.14 | Steering Group | 13Q? | NA
Assessment of Current Provision
13 | Map current provision of all providers of pharmaceutical/dispensing services | 2.5 months | 16.06.17 | 31.08.17 | LA
14 | Identify provision from across HWB boundaries including internet pharmacies | 2 weeks | 01.06.17 | 15.06.17 | LA
15 | Identify service provision over 24 hour period | 1 day | 15.06.17 | 15.06.17 | NHS England
16 | Determination of Dispensing Doctors provision and statement of provision | 1 day | 15.06.17 | 15.06.17 | NHS England
17 | Identification of other pharmaceutical services provided by other NHS providers | 1 day | 15.06.17 | 15.06.17 | CCGs / NHS E
18 | Identify future needs and consider Out of Hospital Strategies | 1 month | 1.7.17 | 1.8.17 | LA
Identification of Gaps in Service Provision
19 | Identification of immediate gaps in service provision by type of provider and by health need | 1 week | 7.10.17 | 14.10.17 | Steering Group
20 | Identification of future needs and gaps in service provision | 1 week | 7.10.17 | 14.10.17 | Steering Group
21 | Determine if patients have reasonable choice in obtaining pharmaceutical services | 1 week | 7.10.17 | 14.10.17 | Steering Group
| Leadership | Duration (in working days) | Start Date | End Date | Individual responsible for completing task | Expected results/Notes | Achieved
Mapping
22 | Maps of defined localities, dispensing services and pharmaceutical services against a range of indices | 2.5 months | 16.06.17 | 31.08.17 | LAs
23 | Maps of accessibility and transportation to services | 2.5 months | 16.06.17 | 31.08.17 | LAs
24 | Maps of cross border commissioning of pharmaceutical services DACs and Internet pharmacies | 2.5 months | 16.06.17 | 31.08.17 | LAs
25 | Determination of directed services for exempt applications | 2.5 months | 16.06.17 | 31.08.17 | LAs | Identified on maps??
Partnerships and marketing
26 | Consult with stakeholders & public in accordance with regulation 3F | 3.5 month | 15.10.17 | 31.01.18 | LA Comms | Comments on final draft to be included |  | This section to be completed after Comms plan finalised in March steering groupn meeting
27 | Determine consultation process, develop consultation form and select questions we want comments on | 1 week | 10.8.17 | 17.8.17 | LA Comms
28 | Arrange Consultation event across HWB for stakeholders and develop crib sheet to answer questions | 1 week | 15.11.17 | 15.12.17 | LA Comms
29 | Communications strategy to keep stakeholders informed of progress and process | Ongoing | 1.2.17 | 1.3.17 | LA Comms | Stakeholders kept informed as to progress
30 | Ensure HWB, LAs, NHS Engalnd and CCGs utilise PNA for all commissioning decisions | Ongoing | 01.04.18 | Ongoing | Steering Group | Pharmacy integrated into commissioning plan
31 | Highlight PNA as example of best practice to PCC, PSNC, LPC & NHS Northwest | Ongoing | Ongoing | Ongoing | LPN
32 | Inform and share progress with neighbouring HWB and LAs | Ongoing | 15.11.17 | 15.12.17 | Steering Group | Requirement of regulations
Finance and Resource
33 | Recognise financial climate when determining recommendations and service redesign | Ongoing | 1.9.17 | 1.10.17 | Finance LA NHS E | Commissioned services align with budgets. In commissioning section of PNA, use 2015 statement
Policy and Strategy
34 | Reflect, align and integrate PNA into JSNA and commissionier strategic plans | Ongoing | 1.9.17 | 1.10.17 | Steering Group
35 | Determine criteria for issuing supplementary statements and subsequent revisions | 1 week | 07.02.17 | 07.03.17 | NHS E / LA | Establish process with H&WB |  | Discussion post-PNA
Key Performance Results, Monitoring
36 | PNA becomes reference document for determining contract applications | Ongoing | TBC | Ongoing | NHS England | PSRC utilise document
37 | Commissioning of pharmaceutical services are supported by PNA findings and commissioning toolkit | Ongoing | TBC | Ongoing | LPN /Commissioners
Key Milestones
38 | Paper to HWB to support PNA Process |  | 07.02.17 | 30.04.17 | NHS England / LA
39 | Project Leads identified and PNA Steering Group established |  | 01.11.17 |  | LA and NHS E
40 | Communications strategy established and published on website |  | 01.03.17 | 31.03.17 | LA
41 | Full Assessment of local need completed |  | 10.4.17 | 18.8.17 | LA
42 | Full Assessment of current provision completed |  | 10.4.17 | 18.8.17 | NHS England
43 | Identification of gaps in service |  |  | 14.10.17 | Steering group
44 | Maps of service providers against a range of markers |  | 16.6.17 | 31.8.17 | LA
45 | Circulate draft PNA document for comments for 30 days with stakeholders (CCGs, NHS England, LA commissioners) |  | 15.10.17 | 14.11.17 | LA
46 | 0 |  | 1.12.17 | 31.01.18 | Steering group
47 | Submit Document to HWB for sign off |  | 1.03.18 |  | Steering group
48 | Annual review and issuing supplementary statements |  |  |  | Steering group
Chapter 1
Chapter 2
Chapter 3
Chapter 4
Chapter 5
Chapter 6
From 1st April 2013, statutory responsibility for publishing and updating a statement of the need for pharmaceutical services passed to health and wellbeing boards (HWBs). Pharmaceutical Needs Assessments (PNAs) are used when considering applications for new pharmacies in an area and by commissioners to identify local health needs that could be addressed by pharmacy services. HWBs have a duty to ensure revised PNAs are in place by April 2018. The coordination and production of the pan-Lancashire PNA covering the three upper tier local authorities has been delegated to a steering group of partners. This collaborative approach gives ownership of the PNA process across the three localities and aims to encourage the widest range of stakeholders and those with an interest in the PNA to participate in its development.This project plan will be monitored by the PNA steering group.

## Gant Chart 2 (hidden)
Gant Chart for the production of a Pharmaceutical Needs Assessment
|  | Duration (in days) | Deadline for Completion | Dec-March | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February
Op - Plan Ref No | WorkStream |  |  |  | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4
1-5. | Leadership and Capacity | 1 month | 1.3.14
13 | Identify current provision of all providers of pharmaceutical/dispensing services | 3 months | 18.6.14
14 | Identify provision from across HWB boundaries including internet pharmacies | 1 month | 1.5.14
7 | Statement as to how the localities have been defined/determined | 2 days | 16.5.14
15 | Identify service provision over 24 hour period | 1 day | 16.5.14
11 | Identify Patient, GP and Pharmacists perception of current and future pharmaceutical services | 2 months | 1.7.14
21 | Maps of defined localities, dispensing services and pharmaceutical services against a range of indices | 1 month | 18.6.14
23 | Maps of controlled localities, reserved localities and LPS designations | 1 month | 18.6.14
6 | Introduction & Define Pharmaceutical Services for PNA | 5 days | 16.6.14
8 | Identify the differing needs of the populations within HWB linked to JSNA | 10 days | 18.6.14
9 | Identify specific communities with poor health e.g. migrant workers, travellers and any seasonal trends | 2 week | 18.6.14
10 | Benchmark localities against comparable populations | 2 week | 18.6.14
16 | Determination of Dispensing Doctors provision and statement of provision | 1 week | 18.6.14
17 | Identification of other pharmaceutical services provided by other NHS providers | 2 weeks | 18.6.14
22 | Maps of accessibility and transportation to services | 2 weeks | 18.6.14
24 | Maps of cross boarder comissioning of pharmaceutical services DACs and Internet pharmacies | 1 week | 18.6.14
12 | Ensure Regulation 3G has been satisfied when assessing need | 1 month | 1.7.14
26 | Develop commissioning strategy from PNA findings | 1 month | 14.7.14
18 | Identification of immediate gaps in service provision by type of provider and by health need | 1 week | 7.7.14
19 | Identification of future needs and gaps in service provision | 1 week | 7.7.14
20 | Determine if patients have reasonable choice in obtaining pharmaceutical services | 1 week | 7.7.14
25 | Determination of directed services for exempt applications | 1 month | 1.7.14
| Write PNA including outline of process followed in developing PNA | 1 month | 14.8.14
28 | Determine consultation process, develop consultation form and select questions we want comments on | 1 month | 1.9.14
29 | Arrange Consultation event across PCT for stakeholders and develop crib sheet to answer questions | 1 week | 14.9.14
48 | Draft PNA submitted to the HWB and LPN | 1 week | 20.08.14
49 | Draft PNA updated from HWB and LPN submitted to Board prior to consultation | 1 week | 17.09.14
50 | Circulate draft PNA document for consultation with stakeholders in accordance with regulation 3F | 60 days | 20.9.14
30 | Communications strategy to keep stakeholders informed of progress and process, webpage | Ongoing | ongoing
35 | Reflect, align and integrate PNA into JSNA and strategic plans | Ongoing | 1.11.14
| Make Ammendments to PNA following responses to consultation | 2 weeks | 14.10.14
51 | Submit Final draft to LPN | 1 week | 1.11.14
52 | Submit Document to HwB for sign off | 1 week | 1.12.14
| Lead | Workstream Colour
Jan Ledward
Stephen Gough
Jim Mechan
Peter/Elaine/Jum/Stephen
Community engagement Jeremey Scholey
Peter Tinson
Ken John
Liz Payne

## Actions (hidden)
Reference in PCT Guidance |  | Action Required | Deadline
Chapter 1 - Intro | 38-46 | Define pharmaceutical services | 31st May
| 47-50 | Determine procedure for Board sign off
|  | - Draft PNA for approval prior to board | 20th August Papers for meeting on 2nd Sept
|  | - Approved paper to Board prior to consultation | 17th September for meeting on 30th Sept
Chapter 2 - Timelines | 5.-7. | Consider criteria / process for subsequent revisions of PNA | 30th July
| 8.-14 | Consider criteria / process for issuing supplementary statements | 30th July
Chapter 3 - Localitites | 7 | Statement explaining how HWB has determined the localities | 14th June
| 11 | Publish Maps of controlled localitites, reserved localities and LPS designations | 18th June
| 13-18 | Define and publish map of localities | 1st May
| 20-24 | Consider cross boarder comissioning and provision of services including DAC and internet pharmacies | 14th July
Chapter 4 - Content of PNA | 2 | Ensure Regulation 3G has been satisified | 18th June
| 5.-9. | Identify season trends, holiday makers and travellers, benchmark comparable populations | 18th June
| 10-19. | Map current provision of pharmaceutical services in an outside of HWB | 18th June
| 16 | Identify provisoin over 24 hour period | 18th June
| 20 | Produce statement of dispensing services provided by GPs | 18th June
| 21 | Identify other providers of pharmaceuutical services not on the pharmaceutical list | 18th June
| 22-26 | Identify gaps in service provision by service type as well as health need | 7th July
| 27-30 and 14-15 Chptr 6 | Identify future needs of the population with respect to pharmaceutical services | 7th July
| 31-36 | Publish Maps of providers of pharmaceutical services and other NHS providers of pharmaceutical services | 18th June
| 37-39 | Determine the advanced and enhanced services exempt applications are to provide | 7th July
Chapter 5 - Consultation | 18-30 | Consult with stakeholders in accordance with Regulation 3F | 20th August
| 27 | Develop questions to prompt responses and develop consultation form | 20th August
|  | Plan Consultation Events across the PCT and develop crib sheet to answer any questions | 18th June
Communications team to lead on this
Chapter 6 - Matters for Consideration | 6-10. | Have regard for reasonable choice in obtaining pharmaceutical services | 7th July

## Section checklist
PNA 2018 Section Checklist
Chapter | Section number | Section Name | Status | Responsibility | Notes | Deadline | Key
1 |  | Key messages | Green | SB |  |  |  | Complete
1 | 1.1 | What is a Pharmaceutical Needs Assessment? | Green |  |  |  |  | To check/underway
1 | 1.2 | What is the purpose of the PNA? | Green | Working group |  |  |  | Not written
1 | 1.3 | Legislative background | Green | MH and ML
1 | 1.4 | What are NHS pharmaceutical services? | Green | MH and ML
1 | 1.5 | Local pharmacy services | Green
1 | 1.5.1 | Public health services | Green | FA
1 | 1.5.2 | NHS England | Green | MH and ML | Check definition of enhanced services with NHS England
1 | 1.5.3 | Clinical Commissioning Groups (CCGs) | Green | EB
1 | 1.6 | What are pharmaceutical lists? | Green
1 | 1.7 | What information will this PNA contain? | Green
2 |  | Key messages | Green | Steering group | Consultation summary to complete (eg, dates and public consultation event)
2 | 2.1 | Summary of the process followed in developing the PNA | Green | MR
2 | 2.2 | Stakeholders involved in the development of the PNA | Green | SB
2 | 2.3 | How stakeholders were involved | Green | FA
2 | 2.4 | Localities used for considering pharmaceutical services | Green | SB
2 | 2.5 | Methods for identifying providers of pharmaceutical services | Green | FA
2 | 2.6 | Assessment of need for pharmaceutical services | Green
2 | 2.7 | Local impact of the new national pharmacy contract (2016) | Green | MH and ML | May be more to add based on Cambridge
2 | 2.8 | Future PNAs and supplementary statements | Green | MR
3 |  | Key messages | Green | MR | Mike to update LE gap
3 | 3.1 | Joint Strategic Needs Assessments | Green | MR | Reflect pan-Lancashire
3 | 3.2 | Lancashire Health and Wellbeing Board | Green | Working group
3 | 3.3 | Lancashire Clinical Commissioning | Green | FA
3 | 3.4 | STP |  | SW | Sheena's narrative on STP has been included here
3 | 3.5 | Outcomes Frameworks | Green | MR
3 | 3.6 | Locations in Lancashire | Green | MR
3 | 3.7.1 | Demography | Green | SB | Population projection paragragh
3 | 3.7.2 | Ethnicity | Green | SB
3 | 3.7.3 | Deprivation | Green | SB
3 | 3.7.4 | Health | Green | FA
4 |  | Key messages | Green | Review number -working grp
4 | 4.1.1 | Community pharmacies | Green | ML
4 | 4.1.2 | Dispensing GP practices | Green | FA & SB | FA to update dipensing practices pop and SB to update table
4 | 4.1.3 | Distance selling pharmacies | Green | ML
4 | 4.1.4 | Dispensing Appliance Contractors | Green | PNA working group | Add sentence from questionaire
4 | 4.1.5 | Hospital pharmacies | Green | PNA working group
4 | 4.1.6 | Pharmacy services in prisons | Green
4 | 4.1.7 | Essential Small Pharmacy Local Pharmaceutical Services (ESPLPS) scheme | Green | MH and ML
4 | 4.1.8 | Comparison with findings in the 2011 PNA | Green | FA | Update locality list for the 14 localities - link postcode to LA
4 | 4.1.9 | Comparison with pharmaceutical service provision elsewhere | Green | ML | Check if 2014/15 is the latest data
4 | 4.1.10 | Results of questionnaires sent to pharmacies and dispensing GP practices | Green | PNA working group | After questionaire completed. Include Heathwatch survey. Sharps bins?
4 | 4.1.11 | Considerations of service providers available | Green | PNA Steering group | After the rest of the chapter is complete- review all
4 | 4.2 | Accessibility | Green | PNA Steering group | Do we need a Equality Impact Assessment
4 | 4.2.1 | Distance, travel times, and access | Green | ML | Check if most up to date legislation referenced
4 | 4.2.2 | Border areas | Green | MR
4 | 4.2.3 | Opening hours: community pharmacies | Green | MH/ML (to be reviewed by Steering group) | narrative around adequate ccoverage
4 | 4.2.4 | Access for people with disabilities | Green | PNA working group | After questionaire completed
4 | 4.3 | Community Pharmacy Essential Services | Green | ML
4 | 4.3.1 | Public health campaigns | Green | ML | Are we taking out the list of campaigns?
4 | 4.4 | Advanced Services | Green | MH and ML
4 | 4.5 | Enhanced Services | Green | ML
4 | 4.6 | Local Improvement Services | Green | EB | Need CCG services
| 4.6.1 | LA PH services | Green
| 4.6.2 | CCG services | Green | EB to review
4 | 4.7 | Pharmacy Facilities / New Developments | Green | ML | EPS
5 |  | Key messages | Green | PNA working group | Check text with Kath
5 | 5.1.1 | Local contributions to improving health and reducing inequalities | Green | FA/KG | Check strategy
5 | 5.1.2 | Evidence based approach | Green
5 | 5.1.3 | Opportunities for integrated care | Green | Ask KG | To review
5 | 5.1.4 | Developing the workforce | Green | Ask KG | To review
5 | 5.2.1 | Local health needs | Green | FA
5 | 5.2.2 | Overview of local services | Green | EB (to check CCG services) | Need CCG services refers to table in 4.6.2 also
5 | 5.3.1 | Smoking - Local health needs | Green | FA
5 | 5.3.2 | Smoking - Local services | Green | Liz to review
5 | 5.3.3 | Smoking - Consideration of services | Green | PNA steering group | to sign off
5 | 5.4.1 | Healthy Weight - Local health needs | Green | SB
5 | 5.4.2 | Healthy Weight - Opportunities in local services | Green | Bpool to check | though amber will still go for consultattion
5 | 5.5 | NHS Health Checks | Green | Liz and BwD commissioner to review | MR to check BwD
5 | 5.6.1 | Local health needs: Chlamydia | Green | MR | MR to amalgamate charts
5 | 5.6.2 | Local health needs: HIV/AIDS, gonorrhoea, syphilis and other conditions | Green | MR
5 | 5.6.3 | Sexual Healh - Local services | Green | MR | Commissioners reviewing. Private HIV screening.
5 | 5.6.4 | Sexual Healh - Consideration of services offered | Green | MR to provide EHC pharmacy no. | With commissioners
5 | 5.7.1 | EHC - Local health needs | Green | FA
5 | 5.7.2 | EHC -Local services | Green | MR | With commissioners
5 | 5.7.3 | EHC - Consideration of services offered | Green | MR | With commissioners
5 | 5.8.1 | Alcohol - Local Health Need | Green | FA
5 | 5.8.2 | Alcohol - locals services | Green | MR | With commissioners
5 | 5.8.3 | Drugs - local health needs | Green | SB
5 | 5.8.4 | Drugs - local services |  | BwD check with commissioers | With commissioners
| 5.8.5 | Considerations of service providers available | Green
5 | 5.9.1 | Older people - local health need | Green | FA
5 | 5.9.2 | Older people - local services | Green | PNA working group
5 | 5.10 | LTCs | Green | EB
5 | 5.10.1 | LTCs - local health need | Green | SB
5 | 5.10.2 | LTCs - Consideration of services offered | Green | EB
5 | 5.11 | Mental Health | Green | MR
5 | 5.11.1 | Mental Health - local services | Green | PNA working group | With commissioners. Include apps
5 | 5.11.2 | Mental Health - consideration of services | Green | PNA working group | With commissioners
5 | 5.12 | Healthcare associated infections | Green
5 | 5.13.1 | Medication related harm - local health need | Green | EB to review | MP
5 | 5.13.2 | Medication related harm - local services |  | ML & MH
5 | 5.13.3 | Medication related harm- consideration of local services | Red | EB | MP | Delete 5.13.3 from the consultation document and while out for consultattion ask Emma to update and provide narrative
5 | 5.14 | Migration | Green | FA
5 | 5.15 | Community Pharmacy Minor Ailments Service | Green | EB
5 | 5.16 | Community Pharmacy Palliative Care Service | Green | EB
5 | 5.17 | Community Pharmacy Healthy Start Service | Green
5 | 5.18 | Healthy Living Pharmacies | Green | KG | To review
5 | 5.19 | Further opportunities for community pharmacy | Green | SW
| 6.0 | Key messages | Green | Working group
| 6.1 | Population changes inLancashire | Green | MR | FA - figure 10 and table 13, MR Table 12
| 6.2 | Housing growth | Green | MR | individual LAs
| 6.2.1 | Monitoring of housing developments |  | BwD link | add links to local plans
| 6.2.2 | Factors to consider in relation to needs PNA | Green | Working group
|  | Exec Summary | Green | Working group | Needs sign off by steering grp
|  | Appendices | Green
|  | Communications material | Green |  | Advert, letter to pharmacies, email to neighbours and stakeholders, twitter/FB
|  | CHANGE LPC TO CPL THROUGHOUT DOCUMENT |  | PNA working group