## Operational Plan
Executive Director:
Associate Director:
Lead:
Target Description: Production of Pharmaceutical Needs Assessment (PNA)
|  | Key: |  | Achieved
In progress
Deadline missed or issue raised
Not started yet
Leadership | Duration (in working days) | Start Date | End Date | Organisation responsible for completing task | Expected results/Notes | Achieved
Each LA Lead to identify Exec Director and HWB member to ensure matrix input & ownership | 1 day | 1.09.21 | 1.09.21 | LAs | Check if Exec Director needed
Paper to HWB to raise awareness of PNA and approval of Pan Lancs PNA steering group | 1 week | 10.01.20 | 10.01.20 | NHS England/Las | PNA process started before COVID and date to be published delayed from Aprl 2021 to Oct 2022
Pan-Lancashire PNA working group to be formed | 1 month | 1.09.21 | 1.09.21 | LA / NHS E | capacity and resource secured
People (capacity & workforce)
Establish PNA Steering Group and Terms of Reference to meet fortnightly | 1 week | 1.09.21 | 1.09.21 | LA/ NHS E
Process
Define Pharmaceutical Services for purpose of PNA | 1day | 7.1.22 | 7.1.22 | NHS England | National NHS England to publish list via KHUB. Need to confirm how data provided to SHAPE and timing of publication
Assessment of Local Need
Determine the most appropriate means of defining localities for PNA and produce statement how defined | 1 week | 1.09.21 | 1.09.21 | LA | Statements from last PNAs. H&WB may have opinion. Localities are 12 districts in Lancs. & 2 unitary authorities |  | The PNA regulations requires the PNA to define ‘localities’ to use during this process. For the purpose of the Pan-Lancashire PNA the area is considered in terms of Lancashire County Council's 12 districts and the 2 unitary authorities of BwD and Blackpool. These localities were selected to support local decision making that takes into account the needs for the population in these areas; also see section 3.5. Characteristics of localities are further described in Appendix 2. Where appropraite, information will be presented at small geography level (ward, MSOA) to describe the health and wellbeing needs of local communities.
Identify charactersitics of the population | 2 month | 1.11.21 | 31.12.21 | LA | Complete chapter 3 (PNA 2018) |  | Some for CCGs still to write
Identify specific communities with poor health | 2 week | 7.1.22 | 21.1.22 | LA | Within chapter 5 |  | Contact to be made with commissioners and request pharmacies' commissiond services list on the 1/12/2021
Benchmark localities against comparable populations | 2 week | 1.2.22 | 15.2.22 | NHS E | within chapter 4 - Comparison with pharmaceutical service provision elsewhere
Identify patient and pharmacists perception of current and future pharmaceutical services | 2 months | 3.1.22 | 28.2.22 | LA/LPC | Send electronic survey via PharmOutcomes. Ask Healthwatch to gather views of the public.
Assessment of Current Provision
Identify service provision over 24 hour period (pharmacy opening hours) | 1 day | 8.01.22 | 8.01.22 | NHS England
Determination of Dispensing Doctors provision and statement of provision | 1 day | 8.01.22 | 8.01.22 | NHS England
Identification of other pharmaceutical services provided by other NHS providers | 1 day | 8.01.22 | 8.01.22 | CCGs / NHS E
Identify future needs and consider Out of Hospital Strategies | 1 month | 1.3.22 | 31.3.22 | Commissioners
Identification of Gaps in Service Provision
Identification of immediate gaps in service provision by type of provider and by health need | 1 week | 1.3.22 | 8.3.22 | Steering Group
Identification of future needs and gaps in service provision | 1 week | 1.3.22 | 8.3.22 | Steering Group
Determine if patients have reasonable choice in obtaining pharmaceutical services | 1 week | 1.3.22 | 8.3.22 | Steering Group
Mapping
Map current provision of all providers of pharmaceutical/dispensing services | 2.5 months | 7.1.22 | 21.3.22 | LA
Identify provision from across HWB boundaries including internet pharmacies | 2 weeks | 8.1.22 | 22.1.22 | LA
Maps of defined localities, dispensing services and pharmaceutical services against a range of indices | 2.5 months | 7.1.22 | 21.3.22 | LAs
Maps of accessibility and transportation to services | 2.5 months | 7.1.22 | 21.3.22 | LAs
Maps of cross border commissioning of pharmaceutical services DACs and Internet pharmacies | 2.5 months | 7.1.22 | 21.3.22 | LAs
Determination of directed services for exempt applications | 2.5 months | 7.1.22 | 21.3.22 | LAs
Partnerships and marketing
Consult with stakeholders & public | - | 1.10.21 | 1.10.22 | All | See comms plan |  | This section to be completed after Comms plan finalised in March steering groupn meeting
Communications strategy to keep stakeholders informed of progress and process | Ongoing | 18.10.22 | 1.10.22 | Working group | See comms plan
Ensure HWB, LAs, NHS Engalnd and CCGs utilise PNA for all commissioning decisions | Ongoing | 1.10.22 | Ongoing | Steering Group | Pharmacy integrated into commissioning plan
Highlight PNA as example of best practice to PCC, PSNC, LPC & NHS Northwest | Ongoing | Ongoing | Ongoing | LPN
Inform and share progress with neighbouring HWB and LAs | Ongoing | 1.7.22 | 1.9.22 | Steering Group | Requirement of regulations
Finance and Resource
Recognise financial climate when determining recommendations and service redesign | Ongoing | 1.2.22 | 1.2.22 | Finance LA NHS E | Commissioned services align with budgets. In commissioning section of PNA, use 2018 statement
Policy and Strategy
Reflect, align and integrate PNA into JSNA and commissionier strategic plans | Ongoing | 1.10.22 |  | Steering Group
Determine criteria for issuing supplementary statements and subsequent revisions | 1 week | 1.10.22 | Ongoing | NHS E / LA | Establish process with H&WB |  | Discussion post-PNA
Key Performance Results, Monitoring
PNA becomes reference document for determining contract applications | Ongoing | TBC | Ongoing | NHS England | PSRC utilise document
Key Milestones
Paper to HWB to support PNA Process |  | 10.01.20 | 10.01.20 | NHS England / LA
Project Leads identified and PNA Steering Group established |  | 1.09.21 | 1.09.21 | LA and NHS E
Communications strategy established |  | 18.10.21 |  | LA
Full Assessment of local need completed |  | 1.11.21 | 21.3.22 | LA
Full Assessment of current provision completed |  | 7.1.22 | 21.3.22 | NHS England
Identification of gaps in service |  | 1.3.22 | 8.3.22 | Steering group
Circulate draft PNA document for comments for 60 days with stakeholders (CCGs, NHS England, LA commissioners) |  | 1.7.22 | 1.9.22 | LA
Submit Document to HWB for sign off |  | 20.9.22 |  | Steering group
Annual review and issuing supplementary statements |  | Ongoing |  | Steering group
From 1st April 2013, statutory responsibility for publishing and updating a statement of the need for pharmaceutical services passed to health and wellbeing boards (HWBs). Pharmaceutical Needs Assessments (PNAs) are used when considering applications for new pharmacies in an area and by commissioners to identify local health needs that could be addressed by pharmacy services. HWBs have a duty to ensure revised PNAs are in place by Oct 2022. The coordination and production of the pan-Lancashire PNA covering the three upper tier local authorities has been delegated to a steering group of partners. This collaborative approach gives ownership of the PNA process across the three localities and aims to encourage the widest range of stakeholders and those with an interest in the PNA to participate in its development.This project plan will be monitored by the PNA steering group.

## Gant Chart 2 (hidden)
Gant Chart for the production of a Pharmaceutical Needs Assessment
|  | Duration (in days) | Deadline for Completion | Dec-March | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February
Op - Plan Ref No | WorkStream |  |  |  | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4 | wk 1-2 | wk 2-4
1-5. | Leadership and Capacity | 1 month | 1.3.14
13 | Identify current provision of all providers of pharmaceutical/dispensing services | 3 months | 18.6.14
14 | Identify provision from across HWB boundaries including internet pharmacies | 1 month | 1.5.14
7 | Statement as to how the localities have been defined/determined | 2 days | 16.5.14
15 | Identify service provision over 24 hour period | 1 day | 16.5.14
11 | Identify Patient, GP and Pharmacists perception of current and future pharmaceutical services | 2 months | 1.7.14
21 | Maps of defined localities, dispensing services and pharmaceutical services against a range of indices | 1 month | 18.6.14
23 | Maps of controlled localities, reserved localities and LPS designations | 1 month | 18.6.14
6 | Introduction & Define Pharmaceutical Services for PNA | 5 days | 16.6.14
8 | Identify the differing needs of the populations within HWB linked to JSNA | 10 days | 18.6.14
9 | Identify specific communities with poor health e.g. migrant workers, travellers and any seasonal trends | 2 week | 18.6.14
10 | Benchmark localities against comparable populations | 2 week | 18.6.14
16 | Determination of Dispensing Doctors provision and statement of provision | 1 week | 18.6.14
17 | Identification of other pharmaceutical services provided by other NHS providers | 2 weeks | 18.6.14
22 | Maps of accessibility and transportation to services | 2 weeks | 18.6.14
24 | Maps of cross boarder comissioning of pharmaceutical services DACs and Internet pharmacies | 1 week | 18.6.14
12 | Ensure Regulation 3G has been satisfied when assessing need | 1 month | 1.7.14
26 | Develop commissioning strategy from PNA findings | 1 month | 14.7.14
18 | Identification of immediate gaps in service provision by type of provider and by health need | 1 week | 7.7.14
19 | Identification of future needs and gaps in service provision | 1 week | 7.7.14
20 | Determine if patients have reasonable choice in obtaining pharmaceutical services | 1 week | 7.7.14
25 | Determination of directed services for exempt applications | 1 month | 1.7.14
| Write PNA including outline of process followed in developing PNA | 1 month | 14.8.14
28 | Determine consultation process, develop consultation form and select questions we want comments on | 1 month | 1.9.14
29 | Arrange Consultation event across PCT for stakeholders and develop crib sheet to answer questions | 1 week | 14.9.14
48 | Draft PNA submitted to the HWB and LPN | 1 week | 20.08.14
49 | Draft PNA updated from HWB and LPN submitted to Board prior to consultation | 1 week | 17.09.14
50 | Circulate draft PNA document for consultation with stakeholders in accordance with regulation 3F | 60 days | 20.9.14
30 | Communications strategy to keep stakeholders informed of progress and process, webpage | Ongoing | ongoing
35 | Reflect, align and integrate PNA into JSNA and strategic plans | Ongoing | 1.11.14
| Make Ammendments to PNA following responses to consultation | 2 weeks | 14.10.14
51 | Submit Final draft to LPN | 1 week | 1.11.14
52 | Submit Document to HwB for sign off | 1 week | 1.12.14
| Lead | Workstream Colour
Jan Ledward
Stephen Gough
Jim Mechan
Peter/Elaine/Jum/Stephen
Community engagement Jeremey Scholey
Peter Tinson
Ken John
Liz Payne

## Actions (hidden)
Reference in PCT Guidance |  | Action Required | Deadline
Chapter 1 - Intro | 38-46 | Define pharmaceutical services | 31st May
| 47-50 | Determine procedure for Board sign off
|  | - Draft PNA for approval prior to board | 20th August Papers for meeting on 2nd Sept
|  | - Approved paper to Board prior to consultation | 17th September for meeting on 30th Sept
Chapter 2 - Timelines | 5.-7. | Consider criteria / process for subsequent revisions of PNA | 30th July
| 8.-14 | Consider criteria / process for issuing supplementary statements | 30th July
Chapter 3 - Localitites | 7 | Statement explaining how HWB has determined the localities | 14th June
| 11 | Publish Maps of controlled localitites, reserved localities and LPS designations | 18th June
| 13-18 | Define and publish map of localities | 1st May
| 20-24 | Consider cross boarder comissioning and provision of services including DAC and internet pharmacies | 14th July
Chapter 4 - Content of PNA | 2 | Ensure Regulation 3G has been satisified | 18th June
| 5.-9. | Identify season trends, holiday makers and travellers, benchmark comparable populations | 18th June
| 10-19. | Map current provision of pharmaceutical services in an outside of HWB | 18th June
| 16 | Identify provisoin over 24 hour period | 18th June
| 20 | Produce statement of dispensing services provided by GPs | 18th June
| 21 | Identify other providers of pharmaceuutical services not on the pharmaceutical list | 18th June
| 22-26 | Identify gaps in service provision by service type as well as health need | 7th July
| 27-30 and 14-15 Chptr 6 | Identify future needs of the population with respect to pharmaceutical services | 7th July
| 31-36 | Publish Maps of providers of pharmaceutical services and other NHS providers of pharmaceutical services | 18th June
| 37-39 | Determine the advanced and enhanced services exempt applications are to provide | 7th July
Chapter 5 - Consultation | 18-30 | Consult with stakeholders in accordance with Regulation 3F | 20th August
| 27 | Develop questions to prompt responses and develop consultation form | 20th August
|  | Plan Consultation Events across the PCT and develop crib sheet to answer any questions | 18th June
Communications team to lead on this
Chapter 6 - Matters for Consideration | 6-10. | Have regard for reasonable choice in obtaining pharmaceutical services | 7th July

## Section checklist
PNA 2022 Section Checklist
Chapter | Section number | Section Name | Status | Responsibility | Deadline | Key
1 |  | Key messages | Green |  |  |  | Complete
1 | 1.1 | What is a Pharmaceutical Needs Assessment? | Green |  |  |  | To check/underway
1 | 1.2 | What is the purpose of the PNA? | Green |  |  |  | Not written
1 | 1.3 | Legislative background | Green
1 | 1.4 | What are NHS pharmaceutical services? | Green
1 | 1.5 | Local pharmacy services | Green
1 | 1.5.1 | Public health services | Green
1 | 1.5.2 | NHS England | Green
1 | 1.5.3 | Clinical Commissioning Groups (CCGs) | Green
1 | 1.6 | What are pharmaceutical lists? | Green
1 | 1.7 | What information will this PNA contain? | Green
2 |  | Key messages | Amber | Working Group | To add date of consultation
2 | 2.1 | Summary of the process followed in developing the PNA | Green
2 | 2.2 | Stakeholders involved in the development of the PNA | Green
2 | 2.3 | How stakeholders were involved | Amber | Working Group | To add date of consultation
2 | 2.4 | Localities used for considering pharmaceutical services | Green
2 | 2.5 | Methods for identifying providers of pharmaceutical services | Green
2 | 2.6 | Assessment of need for pharmaceutical services | Green
2 | 2.7 | Local impact of the new national pharmacy contract (2016) | Red | ML | To review
2 | 2.8 | Future PNAs and supplementary statements | Green
3 |  | Key messages | Green
3 | 3.1 | Joint Strategic Needs Assessments | Green
3 | 3.2 | Lancashire Health and Wellbeing Board | Green
3 | 3.3 | Lancashire Clinical Commissioning Groups | Green | AK | Need to swop order
3 | 3.4 | STP | Green | EC | Need to swop order - Need to add to master document
3 | 3.5 | Outcomes Frameworks | Green
3 | 3.6 | Locations in Lancashire | Green
3 | 3.7.1 | Demography | Green
3 | 3.7.2 | Ethnicity | Green
3 | 3.7.3 | Deprivation | Green
3 | 3.7.4 | Health | Green
4 |  | Key messages | Green
4 | 4.1.1 | Community pharmacies | Green
4 | 4.1.2 | Dispensing GP practices | Green
4 | 4.1.3 | Distance selling pharmacies | Green
4 | 4.1.4 | Dispensing Appliance Contractors | Green
4 | 4.1.5 | Hospital pharmacies | Green
4 | 4.1.6 | Pharmacy services in prisons | Green
4 | 4.1.7 | Essential Small Pharmacy Local Pharmaceutical Services (ESPLPS) scheme | Green
4 | 4.1.8 | Comparison with findings in the 2018 PNA | Green
4 | 4.1.9 | Comparison with pharmaceutical service provision elsewhere | Green
4 | 4.1.10 | Results of questionnaires sent to pharmacies and dispensing GP practices | Green
4 | 4.1.11 | Results of pharmacy users consultation | Amber | PNA working group | Need link to report on Healthwatch website
4 | 4.1.12 | Considerations of service providers available | Green
4 | 4.2 | Accessibility | Green
4 | 4.2.1 | Distance, travel times, and access | Green
4 | 4.2.2 | Border areas | Green
4 | 4.2.3 | Opening hours: community pharmacies | Green
4 | 4.2.4 | Coverage | Green
4 | 4.2.5 | Service provision by population density
| 4.2.6 | Access for people with disabilties |  | PNA working group
4 | 4.3 | Community Pharmacy Essential Services | Green
4 | 4.3.1 | Public health campaigns | Green
4 | 4.4 | Advanced Services | Green
4 | 4.5 | Enhanced Services | Green
4 | 4.6 | Local Improvement Services | Green
| 4.6.1 | LA PH services | Green | EC
| 4.6.2 | CCG services | Red | FA | Add in source of website and CCGs
4 | 4.7 | Pharmacy Facilities / New Developments | Green
5 |  | Key messages | green |  | Check BwD - Done EC
5 | 5.1.1 | Local contributions to improving health and reducing inequalities | Amber | SB | Check references / Refs need updating
5 | 5.1.2 | Evidence based approach | Amber | SB | Check references / Refs need updating
5 | 5.1.3 | Opportunities for integrated care | Amber | SB | Check references / Refs need updating
5 | 5.1.4 | Developing the workforce | Amber | ML | To respond to Kath's comment
5 | 5.2.1 | Local health needs |  |  | FA updated - Done
5 | 5.2.2 | Overview of local services | Red | FA | Add in source of website and CCGs
5 | 5.3.1 | Smoking - Local health needs | Green
5 | 5.3.2 | Smoking - Local services | Green
5 | 5.3.3 | Smoking - Consideration of services | Green
5 | 5.4 | COVID-19
5 | 5.5 | Flu | Amber | ML | Include number of vaccinations form ML | No numbers
5 | 5.6.1 | Healthy Weight - Local health needs | Green
5 | 5.6.2 | Healthy Weight - Opportunities in local services | Green
5 | 5.7 | NHS Health Checks | Green
5 | 5.8.1 | Local health needs: Chlamydia | Amber |  | FA updated - Done
5 | 5.8.2 | Local health needs: HIV/AIDS, gonorrhoea, syphilis and other conditions | Green
5 | 5.8.3 | Sexual Healh - Local services | Green
5 | 5.8.4 | Sexual Healh - Consideration of services offered | Green
5 | 5.9.1 | EHC - Local health needs | Green
5 | 5.9.2 | EHC -Local services | Green
5 | 5.9.3 | EHC - Consideration of services offered | Green
5 | 5.10.1 | Alcohol - Local Health Need | Amber |  | FA updated - Done
5 | 5.10.2 | Alcohol - locals services | Green
5 | 5.10.3 | Drugs - local health needs | Green
5 | 5.10.4 | Drugs - local services
| 5.10.5 | Considerations of service providers available | Green
5 | 5.11.1 | Older people - local health need | Green |  | Done
5 | 5.11.2 | Older people - local services | Amber |  | Done - reviewed, no changes made
5 | 5.12 | LTCs | Green
5 | 5.12.1 | LTCs - local health need | Amber |  | Add new figures - Done
5 | 5.12.2 | LTCs - Consideration of services offered | Green |  | FA updated - Done
5 | 5.13 | Mental Health | Green
5 | 5.13.1 | Mental Health - local services | Amber | FA | FA to check numbering
5 | 5.13.2 | Mental Health - consideration of services | Green
5 | 5.14 | Healthcare associated infections | Green
5 | 5.15.1 | Medication related harm - local health need | Red | ML
5 | 5.15.2 | Medication related harm - local services | Red | ML to review
5 | 5.15.3 | Medication related harm- consideration of local services | Red | this has been deleted from PNA 2022
5 | 5.16 | Migration | Red | EC/SB/FA | Looking for info re: refugees/asyum seekers
5 | 5.17 | Community Pharmacy Minor Ailments Service | Red | Kath has reviewed
5 | 5.18 | Community Pharmacy Palliative Care Service | Red | Working group
5 | 5.19 | Community Pharmacy Healthy Start Service | Green
5 | 5.20 | Further opportunities for community pharmacy | Green
| 60 | Key messages | Green
| 6.1 | Population changes in Lancashire | Green
| 6.2 | Housing growth | Amber |  | Check BwD - complete EC
| 6.2.1 | Monitoring of housing developments
| 6.2.2 | Factors to consider in relation to needs PNA | Green
|  | Exec Summary | Green
|  | Appendices | Green
|  | Communications material | Green
CHANGE LPC TO CPL THROUGHOUT DOCUMENT
|  | EXEC SUMMARY AND RECOMMENDATIONS |  | Steering Group